## Sheet1
ID | Task Name | Status | Est. Duration (Day) | Planned Start | Due Date | Remarks / Deliverables
1 | Project Setup & Analysis | completed
2 | UI / UX Development | completed
2.1 | pre-order flow | completed
2.2 | scan new item flow | completed
3 | Backend Development | pending | 6 | 2026-04-02 | 2026-11-02
3.1 | Project Setup & Repository Initialization | completed | 1 | 2026-04-02 | 2026-05-02 | Setup asp.net core with angular solution and configuring 2 app registrations in azure in order to connect and initiate data flow from crm
3.2 | Authentication/Authorization for desktop | completed | 1 | 2026-05-02 | 2026-08-02 | implement microsoft login
3.3 | Authentication/Authorization for mobile | in progress | 1 | 2026-08-02 | 2026-09-02 | helping the mobile team successfully implement microsoft login
3.4 | Dynamic Inventory implementation | pending | 1 | 2026-09-02 | 2026-11-02 | implementation of dynamic inventory items
3.5 | CRM Updates | pending | 2 | 2026-11-02 | 15/2/2026 | Updating CRM with required fields
4 | NFC Integration | pending | 4 | 15/2/2026 | 19/2/2026
4.1 | Implement NFC support into project | pending | 2 | 15/2/2026 | 17/2/2026
4.2 | Add/Register items through NFC | pending | 2 | 17/2/2026 | 19/2/2026
5 | Testing & QA | Pending | 2 | 19/2/2026 | 22/2/2026 | Unit tests + integration tests
5.1 | Angular Unit Testing | Pending | 1 | - | -
5.2 | API Integration Testing | Pending | 1 | - | -
6 | Deployment & Documentation | Pending | 1 | 22/2/2026 | 23/2/2026 | Release version 1.0
6.1 | DevOps Pipeline + Build Deployment | Pending | 0.5 | - | -
6.2 | Technical Documentation | Pending | 0.5 | - | -
| TOTAL | Pending | 13 | 2026-04-02 | 23/2/2026 | -